## Product Backlog
Final PoC Project | [6 empty] | Story point estimation
# | REQ ID | Features / Requirements - Level 1 | Features / Requirements - Level 2 | Release Phase/Milestone | Priority | Status | Initial Estimation | Sprint |  | Remarks
[7 empty] | 0 | S1 | S2
[7 empty] | 39 | 0 | 0
Application Management / Administration
1 | REQ1 | Login
|  |  | Login UI | Release-1 | P1 | Completed | 9
|  |  | Login Testing | Release-2
2 | REQ2 | Admin Management
|  |  | Admin Login | Release-1 | P1 | In-Progress | 10
|  |  | Register User | Release-1 |  | Completed | 12
|  |  | View User | Release-1 |  | Completed | 8
|  |  | Modify User | Release-1 |  | Completed | 9
|  |  | Delete User | Release-1 |  | Completed | 9
|  |  | Add Floor Numbers | Release-1 |  | Completed | 10
|  |  | Delete Floor Numbers | Release-1 |  | Completed | 9
|  |  | Modify Floor Numbers | Release-1 |  | Completed | 9
|  |  | View Floor Numbers | Release-1 |  | Completed | 8
|  |  | Add Seat Number | Release-1 |  | Completed | 10
|  |  | Modify Seat Number | Release-1 |  | Completed | 15
|  |  | Delete Seat Number | Release-1 |  | Completed | 10
|  |  | View Seat Number | Release-1 |  | Completed | 20
|  |  | Approve/Reject/Pending Requests | Release-2
|  |  | Download Attendance Report | Release-2
|  |  | add parking slots availability | Release-2
|  |  | delete parking slots | Release-2
|  |  | view slots availability | Release-2
3 | REQ3 | User Management
|  |  | User Login | Release-1 |  | Completed | 12
|  |  | View DashBoard | Release-1 |  | Completed | 18
|  |  | View Profile | Release-1 |  | Completed | 15
|  |  | Edit Profile | Release-1 |  | In-Progress | 8
|  |  | Settings | Release-2
|  |  | Notification | Release-2
4 | REQ4 | User Booking Management
|  |  | View Available Seats | Release-1 |  | In-Progress | 10
|  |  | Book Previous Seats | Release-2
|  |  | Enter Details [place,branch,shift,date] | Release-1 |  | Completed | 9
|  |  | Select Seat [floor and seat number] | Release-1 |  | Completed | 12
|  |  | Opt for Food | Release-2
|  |  | Flexible booking [custom/ Daily or weekly] | Release-2
|  |  | generate QR/OTP | Release-2
|  |  | show security key | Release-1 |  | Completed | 15
|  |  | select parking slot | Release-2
|  |  | cancel parking slot | Release-2
|  |  | View Available Slots | Release-2
5 | REQ5 | Security Management
|  |  | Security Login | Release-1 |  | Completed | 14
|  |  | Sacn QR code | Release-2
|  |  | Enter OTP/security key | Release-2
|  |  | display user details | Release-2
6 | REQ6 | Application UI
|  |  | Admin UI Part 1 | Release-1 |  | Completed | 27
|  |  | security UI | Release-2
|  |  | User UI Part 1 | Release-1 |  | Completed | 39
7 | REQ7 | Testing
|  |  | Admin testing | Release-1 |  | Completed
|  |  | Security testing | Release-1 |  | Completed
|  |  | User testing | Release-1 |  | Completed | 6
8 | REQ8 | Deployment
|  |  | setup CI pipeline | Release-1 |  | Completed | 30
|  |  | Release Notes 1 | Release-1 |  | Completed | 12
9 | REQ9 | Unplanned
Buffer Time
UI Buffer Time
Backend Buffer Time
|  | Forgot Password |  |  |  | Completed
|  | LogOut |  |  |  | Completed

## Logs
|  | Thu | Fri | Mon | Tue | Wed | Thu
|  | 2023-03-23 | 2023-03-24 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30
Sl No. | Team | 1 | 2 | 3 | 4 | 5 | 6
1 | Harshjeet Kumar | 5.5 | 6 | 5 | 6 | 7 | 7
2 | Chandan M | 6 | 6 | 5.5 | 6.5 | 7 | 6
3 | Kiran Mahalingappa Hegganadavara | 6 | 6.5 | 5 | 7 | 6.5 | 6
4 | Prabhu Udagatti | 5 | 5.5 | 6 | 7 | 7 | 6.5
5 | Bhoomika C M | 5 | 6 | 6 | 7 | 6.5 | 6.5
6 | Sandhya Sai | 5 | 5 | 6 | 6.5 | 6.5 | 7
7 | Praveen Rajendran | 5.5 | 6 | 5.5 | 6.5 | 6.5 | 6
8 | Sharan R | 6 | 7 | 8 | 7 | 6.5 | 6
9 | Sneha Satish | 5.5 | 7 | 8 | 7 | 7 | 6.5
10 | Jayadharshini N | 5 | 5.5 | 6 | 7 | 6.5 | 7

## Burndown
Iteration | 0 | 2
Remaining | 39 | 0

## Release Phase
# | Release Phase/Milestone | Description
1 | Release-1 | Sprint-1 Release
2 | Release-2 | Sprint-2 Release