## Sprint-4.0 Retrospection
Project Name: TEAM 4 - Office Seat Booking
Sprint - 2.0 |  | 2023-04-07
# | +ve | r | Action Item | Target Date | Responsible
1 | 95% of the planned tasks are completed | unable to finish a couple of tasks | Time management could have been concentrated more. | 07-APR-2023(Sprint - 2) | Team
2 | The co-ordiantion between the frontend and Backend was appericiable. | Active Participation of a few team members could have been better. | Team members should come forward and take a few responsibilities. | 07-APR-2023(Sprint - 2) | Team
3 | The integration part went well |  |  | 07-APR-2023(Sprint - 2) | Team
4 | Extra efforts and learnings are notable. |  |  | 07-APR-2023(Sprint - 2) | Team
5 | Deploying using CI/CD and Kubernetes. | Limited Azure Credits. | Resources should have been used only in production. | 07-APR-2023(Sprint - 2) | Team
6
7