## Sprint-4.0 Retrospection
Project Name: TEAM 4 - Office Seat Booking
Sprint - 1.0 |  | 2023-04-07
# | +ve | r | Action Item | Target Date | Responsible
1 | 90% of the planned tasks are completed in Sprint -1 | Co-ordination between front-end and back-end for the integration part was not upto the mark. | Good communication and discussion could improve the quality of the work better. | 07-APR-2023(Sprint - 2) | Team
2 | Planning for the sprint was done well | Active Participation of a few team members could have been better. | Team members should come forward and take a few responsibilities. | 07-APR-2023(Sprint - 2) | Team
3 | Team co-ordination went well |  |  | 07-APR-2023(Sprint - 2) | Team
4 | Distribution of the tasks was done before hand. |  |  | 07-APR-2023(Sprint - 2) | Team
5 | Completion of task on time |  |  | 07-APR-2023(Sprint - 2) | Team
6
7